## Slide 1
Commercial Manufacturing of AB-101
Budgetary projection for the September Board
Capacity, lead time and cost for a dedicated seven-suite operation.
CONFIDENTIAL · 14 August 2026

## Slide 2
SUMMARY
Responses to your questions
Artiva Biotherapeutics × Made Scientific · Confidential · 14 August 2026
2
You asked | Our answer
Lead time to 7 commercially-licensed GMP suites | Technology transfer starts 2027 at 201 College Road East or East Norriton, bridging to Princeton 307 for GMP, PPQ and commercial readiness. Made Scientific's initial build-out at 307 — cleanrooms, labs, warehousing and cold storage — completes Q4 2027 – Q1 2028; the Artiva suite build runs 12–15 months from signature of the commercial agreement
Cost through Tech Transfer and PLI / 1st commercial batch (2027–2030) | $10.10M – $17.20M, with program initiation and GMP readiness fee-waived
Cost per batch at 200 L, 20 batches/suite/yr | $380K – $430K all-in — $864 – $977 per vial, inside your <$1,000 target
Suite reservation fee | $0 — against an agreed minimum annual batch commitment
Staffing | Dedicated, not shared. Included in the batch fee
Raw materials | $200K per batch, your assumption, passed through at cost
Other — semi-annual APVs, stability, storage | Included in the batch fee
Made Scientific versus other CDMOs | Made Scientific funds and equips the suites — approximately $85M of build that a standard CDMO charges to the client
Additional finding, on slide 4: the same seven rooms can support approximately 24% more output than the current plan assumes.

## Slide 3
LEAD TIME
Starting now, bridging to 307
Artiva Biotherapeutics × Made Scientific · Confidential · 14 August 2026
3
TRANSFER STARTS IN LICENSED SPACE, THEN BRIDGES INTO 307
2027
Tech transfer starts
201 College Road East or East Norriton
2027–28
Initial build-out complete
Cleanrooms, labs, warehousing, cold storage
12–15 mo
Artiva build to GMP ready
From commercial agreement signature
2030
First commercial batch
PLI-ready, on the dates you set

## Slide 4
THROUGHPUT
Increasing throughput within the same seven rooms
Artiva Biotherapeutics × Made Scientific · Confidential · 14 August 2026
4
The eFeeder suite already achieves ~60 batches a year from a 24-day campaign, because only the 9-day bioreactor step occupies the room. Apply the same logic to drug product — turn one DP suite into a seed room feeding the other four — and the same seven rooms go from 107 to 133 batches a year. Add an eighth room and it is 166.

## Slide 5
COST
Program cost
Artiva Biotherapeutics × Made Scientific · Confidential · 14 August 2026
5
THROUGH TECH TRANSFER, PPQ AND PLI · 2027–2030
$10.10M – $17.20M
Program initiation and GMP readiness are fee-waived
Phase | Year
Technology transfer — ICB, drug product, fill/finish | 2027
Analytical method transfer, qualification and validation | 2027–28
Engineering runs and GMP readiness | 2028
Aseptic process simulation and PPQ campaign | 2029
BLA support, PLI readiness, first commercial batch | 2030
PER BATCH AT 200 L · TIERED ON VOLUME
Annual volume | Conversion | Materials | All-in | Per vial
up to 60 batches | $230K | $200K | $430K | $977
61 – 120 batches | $210K | $200K | $410K | $932
121 – 180 batches | $195K | $200K | $395K | $898
over 180 batches | $180K | $200K | $380K | $864
Every tier sits inside the <$1,000 per vial commercial COGS you have set publicly.
At 8 vials per patient that is $6,909 – $7,818 of drug product cost per patient, against the $8,000 in your own materials.
Suite reservation fee: $0
Charged instead as an agreed minimum annual batch commitment, aligning payment with output rather than with reserved capacity.
All figures ±30%, the tolerance you specified. Materials at $200K per batch is your assumption, carried through at cost.

## Slide 6
WORK PACKAGE BREAKDOWN
The same total, by milestone
Artiva Biotherapeutics × Made Scientific · Confidential · 14 August 2026
6
The identical $10.10M – $17.20M from the Cost slide, decomposed to milestone granularity through Pre-License Inspection to commercial manufacturing.
Milestone | Year | Low | High | Basis
M1 · Program Initiation & Knowledge Transfer | 2027 | Waived |  | Fee waived — as on the eHuT-78P program
M2 · Technology Transfer — Process & Analytical | 2027 | $4.90M | $7.90M | ICB, drug product and fill/finish process transfer; analytical method transfer
M3 · GMP Readiness | 2028 | Waived |  | Fee waived — as on the eHuT-78P program
M4 · Engineering Runs | 2028 | $1.60M | $2.60M | ICB and drug product engineering runs
M5 · Aseptic Process Qualification | 2029 | $450K | $750K | 3 consecutive media fills; semi-annual APS thereafter sits in the batch fee
M6 · Process Performance Qualification | 2029 | $1.90M | $3.80M | eFeeder, ICB, DP and fill/finish PPQ — 3 consecutive successful batches each
M7 · Regulatory & PLI Readiness | 2029–30 | $750K | $1.25M | CMC authoring, PLI prep, mock inspection
M8 · Stability Program | 2027–30 | $500K | $900K | ICH stability protocol, pulls, reporting
M9 · Commercial Manufacturing & Lifecycle | 2030+ | $380K | $430K | All-in per batch under the volume-tiered schedule — see the Commercial Forecast
M1–M8 total: $10.10M – $17.20M, matching the Cost slide exactly. M9 is priced per batch, not a fixed fee — forecast by configuration on the next slide.

## Slide 7
COMMERCIAL FORECAST
Volume-based discount, by configuration
Artiva Biotherapeutics × Made Scientific · Confidential · 14 August 2026
7
Structured the way a volume-discount schedule should read: as commitment grows, the batch fee steps down. Anchored to Made Scientific's throughput options rather than an Artiva demand forecast, as drug product volumes have not been shared.
Illustrative year | Configuration | Ceiling | Commitment | Committed batches | Batch fee | Minimum annual fee | $/vial
2030 (PLI & launch) | Option 1 | 107 | 50% | 54 | $230K | $12.42M | $977
2031 | Option 2 | 133 | 65% | 86 | $210K | $18.06M | $932
2032 | Option 3 | 166 | 80% | 133 | $195K | $25.93M | $898
2033+ | Option 4 | 265 | 90% | 238 | $180K | $42.84M | $864
The fee steps down as committed volume scales — $230K → $210K → $195K → $180K per batch — and every step remains inside your <$1,000/vial commercial COGS target. Materials pass-through is additional at $200K/batch and is not part of the minimum fee.
ASSUMPTIONS STATED EXPLICITLY, NOT IMPLIED
The 2030→2033+ year mapping is Made Scientific's proposed adoption sequence, not a commitment Artiva has made. Commitment levels (50/65/80/90%) are illustrative, not yet negotiated. Batch fees are read from the §2 tier schedule at each year's committed volume, not the configuration's ceiling — you do not get bulk-tier pricing on capacity you have not committed to. The interactive site carries a 5-year ramp you can adjust yourself.

## Slide 8
COMMERCIAL MODEL
Commercial model comparison
Artiva Biotherapeutics × Made Scientific · Confidential · 14 August 2026
8
 | A standard CDMO | Made Scientific
Facility build-out | Charged to you — est. $30M–$40M | Absorbed
Suite fit-out and process equipment | Charged to you — est. $45M–$55M | Absorbed
FTEs / labor | Hire and manage your own — est. $7M–$11M/yr for a dedicated ~45–55 FTE team | Included in the batch fee — no separate hire
Suite reservation fee | Charged, and non-refundable | $0 against a volume commitment
Program initiation | Charged | Waived
GMP readiness (APQ, CQV, equipment maintenance & calibration, EMPQ, etc.) | Charged | Waived
Dedicated program management | Charged — est. $15K/month | Included
Capacity | Shared, multi-client | Dedicated suites
WHY THIS MATTERS FOR A BUILD-VERSUS-BUY DECISION
A seven-suite build is roughly $85M — our own estimate of $30M–$40M facility shell plus $45M–$55M suite fit-out and process equipment. Your FY2025 accounts show $2.6M of property and equipment purchases and $874K of leasehold improvements in total — this would be a capital project about a hundred times anything Artiva has undertaken.
Made Scientific funds both. FTEs are dedicated, not billed separately — their cost sits inside the per-batch fee on the Cost slide, not this comparison.

## Slide 9
Appendix
Process flow, suite floor plan, production strategy options, the open variables, and the basis of estimate.

## Slide 10
APPENDIX A1
Assumed Process Flow
Artiva Biotherapeutics × Made Scientific · Confidential · 14 August 2026
9
eFeeder has no suite in the seven-room plan as originally specified. Consolidating its production into 307 alongside the rest of the process is a proposed move — options TBD.

## Slide 11
APPENDIX A2
Suite floor plan and equipment
Artiva Biotherapeutics × Made Scientific · Confidential · 14 August 2026
10
Schematic, not to scale, based on the 307 layout — decoupled configuration, suite 2 converted from drug product to a shared seed room. Equipment fit-out remains an open item; this reflects our modeling assumptions pending confirmation.

## Slide 12
APPENDIX A3
Production strategy options
Artiva Biotherapeutics × Made Scientific · Confidential · 14 August 2026
11
 | Strategy | Rooms | Batches/yr | Patients/yr | Annual conversion cost
1 | As specified — 1 ICB + 5 DP + 1 F/F, seed in-suite | 7 | 107 | 5,885 | $19.3M
2 | Decoupled seed — same seven rooms | 7 | 133 | 7,315 | $23.9M
3 | Decoupled seed — one additional room | 8 | 166 | 9,130 | $26.6M
4 | East Norriton ballroom build | 12 | 265 | 14,575 | $37.1M
Patients per year assume the proposed Phase 3 regimen of two 4-billion-cell doses, i.e. 8 vials per patient. Your stated commercial reach — 250 clinics at 1–2 patients a month — is 3,000 to 6,000 patients a year, so Option 1 already covers the launch plan and the others create headroom. eFeeder was never one of the seven rooms; consolidating its production into 307 is a proposed move, options TBD.
Decoupling the seed train moves the constraint onto the seed room. One seed room running four concurrent trains supports about 182 batches a year, so Option 4 needs a second — without it, eight drug product suites are throttled to 182.

## Slide 13
APPENDIX A4
Key sensitivity: NK seed density
Artiva Biotherapeutics × Made Scientific · Confidential · 14 August 2026
12
Irradiated feeder cells do not replicate, so every drug product batch consumes them at seed and again at each top-up. Our working assumption puts feeder seeding density at 2.5:1 against CD3⁻CD56⁺ NK cells, which leaves the NK seed for a 200 L run as the open variable.
NK expansion | NK seed for 440B | Feeders at 2.5:1 | DP batches per feeder run | Feeder suites needed
100× | 4.4B | 11.0B | ~1.4 | 1.2
250× | 1.8B | 4.4B | ~3.4 | 0.5
500× | 0.9B | 2.2B | ~6.8 | 0.2
1000× | 0.4B | 1.1B | ~13.6 | 0.1
One dedicated feeder suite covers the full program unless NK expansion runs below about 100-fold. Confirming the NK seed density and the number of feeder top-ups would let us replace this table with a single number.

## Slide 14
APPENDIX A5
Basis of estimate
Artiva Biotherapeutics × Made Scientific · Confidential · 14 August 2026
13
Input | Value | Source
Drug product batch yield | ~440 vials at 1×10⁹ cells | Linear 4× from ≥110B at 50 L (Cytotherapy, 2026)
Batch duration | 11–13 days | Your process summary, August 2026
Batches per suite per year | 20 (in-suite seed) / 33 (decoupled) | Your San Diego operating rate; decoupled figure is our estimate
Feeder campaign | 24 days, ~60 batches/yr per suite | eHuT-78P process and our East Norriton suite assessment
Feeder : NK seeding ratio | 2.5 : 1 | Our working assumption
Dose | 2 × 4 billion cells, 8 vials per patient | Proposed Phase 3 design, 8-K of 8 May 2026
Materials per batch | $200,000 | Your assumption
Commercial COGS ceiling | <$1,000 per 1B-cell vial | Artiva public statements, 200 L process
Estimates pending confirmation: the split of the 11–13 day batch between seed train and 200 L expansion, suite turnaround time, and NK seed density. These move the throughput figures; they do not change the commercial structure.

## Slide 15
CLOSE
Next steps
Artiva Biotherapeutics × Made Scientific · Confidential · 14 August 2026
14
1
Confirm the process assumptions
A short technical session on seed-train duration, suite turnaround and NK seed density would replace our estimates with your numbers and tighten the ±30%.
2
Resolve the suite configuration
Transfer starts at 201 College Road East or East Norriton and bridges into 307. Consolidating eFeeder into 307 is a proposed move, options TBD — and raises one room or two for feeder + ICB, and shared vs. per-suite harvest.
3
Capacity reservation
A reservation agreement secures a technology transfer slot and suite capacity, and is credited in full against work orders.
4
Detailed proposal
On your word we convert this into a work-order-level proposal with a full Gantt to first commercial batch.